VERIFIABLE CREDENTIALING INFRASTRUCTURE

# DaaS Technical Scope

# Alternatives for Governments

Spark   |   Boost   |   Scale

Ref: DaaS Scope Document v2.0

Prepared for: DPI Owner & Ecosystem Stakeholders

Date: February 2026

| SPARK | BOOST | SCALE |
| --- | --- | --- |

SECTION 00

# Contents

Contents	2

SECTION 01	5

Executive Summary	5

SECTION 02	6

Rationale for Technical Scope Alternatives	6

SECTION 03	7

Package Overview	7

SECTION 04	8

Requirements Matrix — Credential Issuance	8

SECTION 05	11

Requirements Matrix — Credential Verification	11

SECTION 06	13

Requirements Matrix — Credential Storage & SSO	13

SECTION 07	14

Requirements Matrix — Programmatic Requirements	14

SECTION 08	16

Requirements Matrix — Non-Functional & New Requirements	16

SECTION 09	18

AI Blocks — DPI Workflows & User-facing Services	18

AI Governance & Responsible Use	18

SECTION 10	19

Timeline Overview by Package	19

SPARK — 16-Week Active Rollout + 10-Week Post-Rollout	19

BOOST — 24-Week Active Rollout + 24-Week Post-Rollout	19

SCALE — 24-Week Active Rollout + 24-Week Post-Rollout	20

SECTION 11	21

Comparative Milestone Summary	21

SECTION 12	22

Costing Framework — Cost Categories	22

SECTION 13	23

Role Definitions & Staffing Model	23

13A. Role Definitions	23

13B. Indicative Staffing Per Tier	24

SECTION 14	25

Estimated Person-Hours by Tier	25

SECTION 15	26

Country Commitments for DaaS Engagement	26

SECTION 16	29

Indicative Cost Structure by Tier	29

SECTION 17	30

Payment Milestone Structure	30

17A. Payment Conditions	30

SECTION 18	31

AI Integration Costing Guidance	31

18A. Scoping Process	31

18B. AI Cost Components	31

SECTION 19	32

Financial Proposal Template	32

SECTION 20	33

Costing Summary Comparison	33

# SECTION 01

## Executive Summary

The current DaaS scope document (v2.0) defines a comprehensive, single-tier engagement for deploying Verifiable Credentialing (VC) infrastructure in a country. It bundles together all technical components (issuance, verification, credential store, SSO), all programmatic deliverables (outreach, ecosystem expansion, sustainability planning), and all support obligations (L1–L3, cloud hosting, training) into one monolithic scope.

This proposal recommends restructuring the DaaS offering into three tiered packages to provide countries with flexibility, lower the barrier to entry, and create a natural progression path from initial deployment to full-scale ecosystem maturity:

| SPARK | BOOST | SCALE |
| --- | --- | --- |
| Minimum viable deployment. 2 end-to-end use cases, foundational infrastructure, compressed 16-week rollout with 10-week post-rollout support. | Closest equivalent to DaaS v2.0. 2–5 use cases, outreach playbook, ecosystem onboarding, national policy support, 24-week rollout with 24-week post-rollout support. | Advanced capabilities and deeper institutional embedding. 5+ use cases, full strategic deliverables suite, ecosystem mapping, 24-week rollout with 24-week post-rollout support. |

Each tier also incorporates a progressive AI capability layer — from AI-assisted development tooling in Spark, through intelligent user-facing services in Boost, to advanced AI-driven ecosystem intelligence in Scale — ensuring that AI is embedded as a force multiplier across the entire credentialing lifecycle.

# SECTION 02

## Rationale for Technical Scope Alternatives

Barrier to Entry. Some countries need to demonstrate feasibility before committing to a full engagement with 2+ use cases. A lighter Spark package lowers the threshold for adoption.

One-Size-Fits-All Pricing. The DaaS for DVC v2.0 technical scope bundles strategic deliverables (national policy drafting, sustainability planning) with technical deployment. Countries at different maturity levels need different things.

Scope Creep Risk. By defining clear tier boundaries, Service Providers and DPI Owners have shared expectations on what is included vs. what constitutes an upgrade.

Gradual Evolution Pathway. Countries that succeed with Spark have a natural upgrade path to Boost and Scale, maintaining momentum and deepening the engagement.

The following sections detail the complete requirements matrix across all three tiers, maintaining full alignment with DaaS v2.0 requirement IDs for traceability.

# SECTION 03

## Package Overview

| Dimension | Spark | Boost | Scale |
| --- | --- | --- | --- |
| Active Rollout | 16 weeks | 24 weeks | 24 weeks |
| Post-Rollout Support | 16 weeks | 24 weeks | 24 weeks |
| Total Engagement | ~8 months | ~12 months | ~12 months |
| Hosting Duration | 8 months | 12 months | 12 months |
| Use Cases at Go-Live | 2 end-to-end | 2–5 end-to-end | 5+ end-to-end |
| L3 Support | — | — | ✓ |
| Outreach Playbook | — | ✓ | ✓ |
| Impact Whitepaper | — | — | ✓ |
| National Policy Support | — | ✓ | ✓ |
| AI for Building DaaS | Basic | ✓ | ✓ |
| AI Services for End Users | Basic | ✓ | ✓ |

# SECTION 04

## Requirements Matrix — Credential Issuance

All CI requirements from DaaS v2.0 Section 8.1, mapped to the tiered model. Primary owner: SP (supported by ISV).

| Req ID | Requirement | Spark | Boost | Scale |
| --- | --- | --- | --- | --- |
| CI-01 | Issuance platform must provide self-service issuer onboarding portal with configurable approval workflows (manual approval, automated verification, hybrid) | ✓ | ✓ | ✓ |
| CI-02 | Issuer onboarding must collect and validate key details eg Legal entity name, registration number, authorized signatories, technical contact details, DID/signing key configuration, geographic jurisdiction | ✓ | ✓ | ✓ |
| CI-03 | Role-based access control must support minimum roles: - Super Admin (platform management), - Issuer Admin (schema/template/user management), - Credential Officer (credential issuance only) - Auditor (read-only access to logs) | ✓ | ✓ | ✓ |
| CI-04 | Issuer profile must auto-generate or allow upload of: DID document (eg did:web, did:key), X.509 certificates, or public keys with automatic trust registry registration | ✓ | ✓ | ✓ |
| CI-05 | Issuance solutions must be offered in at least one of the offerings: - SDK - SaaS offering - Hosted solution | ✓ | ✓ | ✓ |
| CI-06 | Issuance solutions must provide options to configure the following: - Language options - Credential docs (pdf/svg) templates (logo, colour themes, etc.,) - QR code content - Machine readable schema formats (.json, .xml) across multiple VC standards - Data schemas to support multiple credential types | Basic | ✓ | ✓ |
| CI-07 | Issuance solutions must provide capability to generate and store signing keys secure vaults. Additionally, corresponding verification keys must be made available for verification SDKs to verify credentials. | ✓ | ✓ | ✓ |
| CI-08 | Issuance solutions must support issuance in signed qr (svg, etc), signed docs (.pdf, svg, etc) and machine readable format(s) (.json .xml, etc) using popular VC standards (e.g W3C-VC) | ✓ | ✓ | ✓ |
| CI-09 | Issuance solutions must generate credentials in batch/on-demand through standard / popular APIs. | ✓ | ✓ | ✓ |
| CI-10 | Issuance solutions must facilitate excel/csv file upload (of attested individuals' data) to generate credentials and return credential artefacts back to the issuer. | ✓ | ✓ | ✓ |
| CI-11 | Issuance solutions must support issuance of credential in print format with signed QR e.g pdf, svg etc., | ✓ | ✓ | ✓ |
| CI-12 | Issuance solutions must support issuance of the credentials to user controlled credential store either on cloud (eLocker) or mobile (wallet) | ✓ | ✓ | ✓ |
| CI-13 | Issuance solutions must allow issuers to revoke credentials | — | ✓ | ✓ |
| CI-14 | Issuance solutions may optionally allow workflow based credential mgmt for issuance/revocation | — | ✓ | ✓ |
| CI-15 | Issuance solutions must support UI/UX customization, including templates, logo, language and colours, based on issuer requirements | Basic | ✓ | ✓ |
| CI-16 | Issuance solutions must support delegated access to credentials. The system must allow a parent or legal guardian to receive, view, and present the credential on behalf of a minor, and linkage to the child must be validated using authoritative registry data | — | ✓ | ✓ |
| CI-17 | L1, L2, L3 support for credential issuance (SP trained and certified) | L1/L2 | L1/L2 | ✓ |
| CI-18 | L3 support extended 6 months post-rollout (12 months total) | — | — | ✓ |
| CI-19 | Batch issuance: min 10,000 credentials/hour; <2s latency for on-demand | ✓ | ✓ | ✓ |
| CI-20 | Go-live by integrating all the above issuance capabilities with all the identified issuers and respective issuer systems. | All | All | All |

# SECTION 05

## Requirements Matrix — Credential Verification

All CV requirements from DaaS v2.0 Section 8.1, mapped to the tiered model. Primary owner: SP (supported by ISV).

| Req ID | Requirement | Spark | Boost | Scale |
| --- | --- | --- | --- | --- |
| CV-01 | Verification solution must support offering credential verification in below channels: - SDKs / Libraries / Utilities (mandatory) - APIs - Web portals / Mobile apps | ✓ | ✓ | ✓ |
| CV-02 | Verification must validate: - Cryptographic signature using issuer's public key from trust registry, - JSON-LD proof chains for W3C VCs, - Certificate path validation for X.509-based credentials - Revocation status via CRL/OCSP/StatusList2021, - Credential expiry timestamps, - Schema compliance validation | ✓ | ✓ | ✓ |
| CV-03 | Verification solution must support online/offline validations. All interfaces and documentation must be delivered in {select local language as default). Bilingual (xx/EN) support is desirable for interoperability with international verifiers. | ✓ | ✓ | ✓ |
| CV-04 | Verification solution must support in-person/remote acceptance of credentials | ✓ | ✓ | ✓ |
| CV-05 | Verification solution must support self/assisted use cases | ✓ | ✓ | ✓ |
| CV-06 | ZKP-based selective disclosure for credential acceptance | — | — | ✓ |
| CV-07 | Implementing credential verification flows: - SDK integration in accepting entity mobile app - Web app hosted by accepting entity (and/or issuer) | ✓ | ✓ | ✓ |
| CV-08 | Notification infrastructure (mobile, email, app-based etc.) to notify individuals during issuance, storing and verification as defined by respective module admins. | — | ✓ | ✓ |
| CV-09 | L1, L2, L3 support for verification (SP trained and certified) | L1/L2 | L1/L2 | ✓ |
| CV-10 | L3 support extended 6 months post-rollout (12 months total) | — | — | ✓ |

# SECTION 06

## Requirements Matrix — Credential Storage & SSO

All CS and SSO requirements from DaaS v2.0, mapped to the tiered model.

| Req ID | Requirement | Spark | Boost | Scale |
| --- | --- | --- | --- | --- |
| CS-01 | Credential store solution must allow below options with seamless integration with issuance and verification solutions across: - Digital - Personal Computer Local store - Digital - Cloud Store - Digital - eLockers Svc - Mobile - Wallet | ✓ | ✓ | ✓ |
| CS-02 | Credential store solutions must support import of credentials to user controlled stores either on cloud (eLocker) or mobile (wallet) and with one or more authentication modalities. E.g. - Knowledge based auth - OTP auth - Biometric auth - Face auth | ✓ | ✓ | ✓ |
| CS-03 | Credential store solutions must support holding of various types of credentials across issuers and in multiple standards. | ✓ | ✓ | ✓ |
| CS-04 | Credential store solutions must support delegated storing of credentials. E.g., the system must allow a parent or legal guardian to view and present the credential on behalf of a minor, and linkage to the child must be validated using authoritative registry data | — | ✓ | ✓ |
| SSO | SSO integration (eSignet, WSO2, Keycloak, or custom) with - Functional ID provider; - Login options: knowledge-based, OTP, biometric | ✓ | ✓ | ✓ |

# SECTION 07

## Requirements Matrix — Programmatic Requirements

All PR requirements from DaaS v2.0 Section 8.1, mapped to the tiered model.

| Req ID | Requirement | Spark | Boost | Scale |
| --- | --- | --- | --- | --- |
| PR-101 | Meet Technical, Programmatic and Strategic Rollout objectives. More Info Rollout (KRAs) Scope | ✓ | ✓ | ✓ |
| PR-201 | Go live on use-cases (end to end) as identified in section. More Info Program Deliverables (KRAs) Scope | 2 UCs | 2–5 UCs | 5+ UCs |
| PR-202 | Onboarding of at least one additional end-to-end use case and identification of three additional issuer institutions. More Info Program Deliverables (KRAs) Scope | — | ✓ | ✓ |
| PR-203 | Outreach Strategy documented in a playbook, including a roadmap of adoptions by issuers and acceptors beyond the six-month rollout. More info Program Deliverables | — | ✓ | ✓ |
| PR-204 | Publication of a Whitepaper on the Impact of Credentialing as a DPI. More info Program Deliverables | — | — | ✓ |
| PR-301 | Technical deliverables. More Info Technical Deliverables | ✓ | ✓ | ✓ |
| PR-401 | Meet the overall Delivery Schedule. More Info Schedule of Deliverables | ✓ | ✓ | ✓ |
| PR-901 | DPG owners must support SP and ISVs to provide timely release of stable and critical updates to the open source code base and carry out vulnerability and resilience assessments, as well as end-to-end penetration tests on the deployed solutions, in accordance with the NIST cybersecurity framework. | ✓ | ✓ | ✓ |
| PR-902 | DPI owner must align required personnel identified during kick off meeting for successful execution of the roll out | ✓ | ✓ | ✓ |
| PR-903 | DPI owner must make sure required program, technical and operational personnel to take over the solution with a skill transfer as agreed during the kick of meeting | ✓ | ✓ | ✓ |
| PR-904 | DPI owner must lead to facilitate additional roll-out use cases and connect SP and ISVs to successfully implement the program | ✓ | ✓ | ✓ |
| PR-905 | DPI owner must lead to facilitate reliable and resilient hosting of data schema and trust registry of issuers and verifiers in well known place for ecosystem to leverage | ✓ | ✓ | ✓ |
| PR-906 | DPI owner must enable required policies (if any) to enable issuance, revocation, store and acceptance of credential solutions with-in the country. | ✓ | ✓ | ✓ |
| PR-907 | Issuers must provide attested data files and/or access to the data store to generate credentials. | ✓ | ✓ | ✓ |
| PR-908 | Accepting entities must provide support to integrate verification SDKs in web portals and mobile apps to allow credential acceptance. | ✓ | ✓ | ✓ |

# SECTION 08

## Requirements Matrix — Non-Functional & New Requirements

All NFR requirements from DaaS v2.0 Section 8.2 plus new requirements added in the tiered model.

| Req ID | Requirement | Spark | Boost | Scale |
| --- | --- | --- | --- | --- |
| NFR-01 | Thorough integration testing, failover testing; fix critical/major bugs for smooth rollout | ✓ | ✓ | ✓ |
| NFR-02 | Data integrity and credential accuracy assurance | ✓ | ✓ | ✓ |
| NFR-03 | Security best practices for data, information, and systems | ✓ | ✓ | ✓ |
| NFR-04 | Hosting and technical support from implementation kickoff (includes post-rollout period) | 12 mo | 12 mo | 12 mo |
| NFR-05 | Availability and security monitoring | ✓ | ✓ | ✓ |
| NFR-06 | 99.9% uptime SLA | ✓ | ✓ | ✓ |
| NFR-07 | Training, procedures, process documentation, and materials in local language | Basic | ✓ | ✓ |
| NFR-08 | Implementation and integration documentation for DPI Owner | ✓ | ✓ | ✓ |
| NFR-09 | Full source code and technical documentation handover on request | ✓ | ✓ | ✓ |
| NFR-10 | VAPT and cybersecurity framework compliance (per national framework) | — | Basic | ✓ |
| NFR-11 | Iterative UX testing with diverse user groups (low-literacy, rural, guardians) throughout lifecycle | — | ✓ | ✓ |
| NFR-12 | Infrastructure as Code (Terraform) for cloud-agnostic deployment (AWS, GCP, Azure, OCI, on-prem) | ✓ | ✓ | ✓ |
| NFR-13 | Operational and business plan (cost recovery models, workflows, stakeholder roles) | ✓ | ✓ | ✓ |
| NFR-14 | Multilateral funding alignment (national budgets, IDB, World Bank, etc.) | ✓ | ✓ | ✓ |
| NFR-15 | National credentialing policy support | — | ✓ | ✓ |
| NFR-16 | Self-service issuer/verifier onboarding toolkit | ✓ | ✓ | ✓ |
| NFR-17 | Ecosystem mapping and expansion advisory | ✓ | ✓ | ✓ |
| NFR-18 | Data portability and migration tooling (JSON-LD, CSV, migration scripts, validation, etc.) | ✓ | ✓ | ✓ |

# SECTION 09

## AI Blocks — DPI Workflows & User-facing Services

AI capabilities must be designed as optional, composable services that sit alongside — not inside — the core credentialing stack. This ensures that the VC infrastructure remains standards-compliant, auditable, and functional without AI dependencies, while AI services can be progressively activated as the country’s maturity and capacity grow.

### AI Governance & Responsible Use

All AI capabilities must adhere to the following governance principles, applicable across all tiers:

Transparency. AI-generated outputs (e.g., auto-filled forms, risk scores, schema suggestions) must be clearly labelled as AI-generated. Users must be able to review and override AI recommendations before they take effect.

Data Sovereignty. AI models must not transmit personal credential data outside the country’s designated hosting environment. Where cloud-based AI services are used, they must comply with the same data residency requirements as the credential infrastructure itself.

Bias & Fairness. AI models used in fraud detection, risk scoring, or recommendation engines must be regularly audited for bias. The SP must provide documentation of training data sources, evaluation metrics, and bias mitigation measures.

Human-in-the-Loop. No AI system may autonomously reject, revoke, or block a credential without human review. AI outputs serve as decision-support tools, not autonomous decision-makers, particularly in verification and fraud detection workflows.

Open & Interoperable. AI components should use open standards and APIs to avoid vendor lock-in. Where proprietary models are used, the SP must provide documented fallback procedures that maintain full system functionality without the AI layer.

# SECTION 10

## Timeline Overview by Package

Each tier follows a phased engagement model with clearly defined milestones and payment gates.

## SPARK — 16-Week Active Rollout + 10-Week Post-Rollout

Spark delivers 2 end-to-end use cases (2 issuers, corresponding verifiers) with foundational VC infrastructure. The timeline is compressed relative to v2.0, reflecting reduced programmatic scope (no outreach playbook, no ecosystem expansion, no sustainability planning).

| Phase | Weeks | Description | Pay % |
| --- | --- | --- | --- |
| A. Planning & Design | Wk 1–2 | Finalize tech integration, training, and outreach requirements | 20% |
| B. Product Setup & Pilot Go-Live | Wk 3–10 | Installation, integration, config; stakeholder demo (Wk 6); launch | 35% |
| C. Go-Live & Stabilization | Wk 11–14 | Production monitoring, immediate support, bug resolution | 30% |
| D. Transition & Basic Handover | Wk 15–16 | SOPs, system handover, closure report | 15% |
| E. Post-Rollout Support | Wk 17–26 | L1/L2 support, cloud hosting, basic monitoring | incl. |

## BOOST — 24-Week Active Rollout + 24-Week Post-Rollout

Boost is the closest equivalent to the current DaaS v2.0 scope. It deploys 2–5 use cases, includes the outreach playbook, ecosystem onboarding, national credentialing policy support, and L1–L2 support with 12-month cloud hosting.

| Phase | Weeks | Description | Pay % |
| --- | --- | --- | --- |
| A. Planning & Design | Wk 1–2 | Finalize integration, training, outreach requirements | 15% |
| B. Product Setup & Go-Live | Wk 3–10 | Setup, pilot, stakeholder demo (Wk 6), launch | 30% |
| C. Execution & Scaling | Wk 11–24 | Use-case execution, outreach, ecosystem onboarding | 30% |
| D. Transition & Closure | Wk 19–24 | SOPs, handover, policy submission, closure report | 10% |
| E. Post-Rollout Support | Wk 25–48 | L1/L2 support, cloud hosting, monitoring | 15% |

## SCALE — 24-Week Active Rollout + 24-Week Post-Rollout

Scale deploys 5+ use cases within the same 24-week active window as Boost, with denser parallel workstreams. It delivers the full suite of strategic deliverables (operational/business plan, multilateral funding alignment, impact whitepaper, ecosystem mapping), and provides L1–L3 support with 12-month cloud hosting.

| Phase | Weeks | Description | Pay % |
| --- | --- | --- | --- |
| A. Planning & Design | Wk 1–2 | Finalize all requirements; kick off governance | 10% |
| B. Product Setup & Go-Live | Wk 3–10 | Full setup, integration, stakeholder demo, launch | 20% |
| C. Execution & Scaling | Wk 11–24 | Production operations, use-case rollout, outreach | 30% |
| D. Ecosystem, Strategy & Closure | Wk 19–24 | Ecosystem mapping, self-service toolkit, whitepaper, business plan, SOPs, handover, national policy submission | 15% |
| E. Post-Rollout Support (L1–L3 + Hosting) | Wk 25–48 | L1–L3 support, cloud hosting, monitoring, training completion | 25% |

# SECTION 11

## Comparative Milestone Summary

The following table compares key milestones across all three tiers to help DPI Owners and Service Providers understand the pace and depth of each engagement.

| Milestone | Spark | Boost | Scale |
| --- | --- | --- | --- |
| Integration plan signed off | Week 2 | Week 2 | Week 2 |
| Stakeholder demonstration | Week 6 | Week 6 | Week 6 |
| First use cases live in production | Week 11 | Week 10 | Week 10 |
| Outreach playbook published | — | Week 18 | Week 18 |
| Additional use cases onboarded | — | Week 20 | Week 20 |
| Self-service onboarding toolkit live | — | — | Week 22 |
| VAPT completed | — | Week 30 (basic) | Week 22 (full) |
| Impact whitepaper published | — | — | Week 24 |
| Operational/business plan delivered | — | — | Week 22 |
| National credentialing policy submitted | — | Week 22 | Week 23 |
| SOPs finalized & system handed over | Week 16 | Week 24 | Week 24 |
| L3 support ends | — | — | Week 48 |
| Cloud hosting ends | Month 8 | Month 12 | Month 12 |
| Total engagement concludes | Week 26 | Week 48 | Week 48 |

Note: This timeline is a working proposal. Phase durations and milestone dates should be validated against country-specific conditions (e.g., issuer readiness, data availability, policy environment) during the Planning & Design phase of each engagement.

# SECTION 12

## Costing Framework — Cost Categories

This section establishes a standardised, repeatable costing framework for the three DaaS tiered packages. Costs are organised into five primary categories plus an AI placeholder, each traceable to requirements in the tiered model.

| # | Cost Category | Description | Primary Drivers |
| --- | --- | --- | --- |
| I | People Cost | Professional fees for all roles: program management, technical development, operations and support. | Roles, person-hours, local vs. remote, tier duration |
| II | Travel & Logistics | International and domestic travel: flights, visas, vaccinations, insurance, hotel stays, per diem. | Country location, number of visits, stay duration |
| III | Infrastructure & Hosting | Cloud hosting for staging and production environments including compute, storage, networking, monitoring, security. | Cloud provider, hosting duration, data residency, on-prem vs. cloud |
| IV | Tooling & Licensing | Third-party software licences, ISV product fees, DevOps tooling, monitoring, notification gateways, testing tools. | ISV solution choice, notification volumes, testing scope |
| V | Contingency / Flex | A percentage buffer on People Cost (Category I) to absorb scope variation, unplanned integration complexity, or country-specific customisation. | Risk profile, SP experience, scope certainty |
| VI | AI Integration (Placeholder) | Costs for AI capabilities (Section 09, AI-B and AI-U series). Scoped separately per country based on AI readiness assessment. | AI maturity, data sovereignty, model hosting, local AI/ML partners |

Categories I through IV constitute the base engagement cost. Category V is applied as a percentage of Category I (People Cost), consistent with established DaaS engagement precedents. Category VI is excluded from the base cost and must be scoped, assessed, and priced independently for each country.

# SECTION 13

## Role Definitions & Staffing Model

The staffing model suggests a possible scoping of roles, location types, and effort levels for each tier. Roles are grouped into three streams: Program Management, Technical Development, and Technical Operations.

### 13A. Role Definitions

| # | Role | Stream | Responsibilities |
| --- | --- | --- | --- |
| 1 | Program Manager | Program | Accountable for overall rollout implementation against KPIs. Stakeholder alignment and progress reporting. |
| 2 | Adoption Advocacy Manager | Program | Drives end-user adoption and cross-pollination of credentialing across ministries and departments. |
| 3 | Technical Project Manager | Program – Ops | Planning, reporting, and execution of installation, configuration, and extension of the credentialing stack. |
| 4 | Technical Architect / Lead | Tech – Dev | Leads design and execution of installation, configuration, integration, and extension. Mentors the technical team. |
| 5 | Business Analyst / PM | Program | Captures country-specific requirements. Creates training plans, documentation, and functional training sessions. |
| 6 | Outreach Manager | Program | Creates and executes the outreach plan for the rollout in coordination with the DPI Owner. |
| 7 | DevOps Engineer | Tech – Dev | Installation of the credentialing stack on-prem or cloud. Manages NOC/SOC per SLAs. |
| 8 | Full Stack Developer | Tech – Dev | Designs, configures, and extends the stack per requirements. Addresses bugs/issues per SLAs. |
| 9 | QA / Tester | Tech – Dev | Writes test cases, tests, and certifies the product for production readiness. |
| 10 | Service Delivery Lead | Tech – Ops | Technical lead for support and DevOps teams. Reports operational health and adoption metrics. |
| 11 | L1 Support | Tech – Ops | Initial triage, classification of issues, providing workarounds within SLAs. |
| 12 | L2 Support | Tech – Ops | Root cause analysis, impact assessment, bug fixes within SLAs. Contributes fixes back to DPG. |
| 13 | L3 Support | Tech – Ops | Enhances and fixes DPG core code. Implements new use cases. Contributes back to DPG. |

### 13B. Indicative Staffing Per Tier

FT = Full Time (40 hrs/wk). Percentage figures indicate part-time allocation. “—” indicates the role is not included in that tier.

| Role | Location | Spark (16 wk) | Boost (24 wk) | Scale (24 wk) | Stream |
| --- | --- | --- | --- | --- | --- |
| Program Manager | Local/Remote | 12 wk FT + 4 wk 50% | 12 wk FT + 12 wk 50% | 16 wk FT + 8 wk 50% | Program |
| Technical Project Mgr | Remote | 10 wk FT | 12 wk FT | 10 wk FT | Program – Ops |
| Tech Architect / Lead | Remote | 10 wk FT | 12 wk FT | 10 wk FT | Tech – Dev |
| Business Analyst / PM | Remote | 8 wk FT + 4 wk 25% | 12 wk FT + 12 wk 25% | 14 wk FT + 10 wk 25% | Program |
| DevOps Engineer | Remote | 8 wk FT + 4 wk 25% | 12 wk FT + 12 wk 25% | 14 wk FT + 10 wk 25% | Tech – Dev |
| Full Stack Developer | Remote | 8 wk FT | 10 wk FT | 12 wk FT | Tech – Dev |
| QA / Tester | Remote | 6 wk FT | 8 wk FT | 10 wk FT | Tech – Dev |
| Service Delivery Lead | Remote | 50% for 10 wk | 50% for 14 wk | 50% for 24 wk | Tech – Ops |
| L1 Support | Remote | 10 wk FT | 14 wk FT | 24 wk FT | Tech – Ops |
| L2 Support | Remote | 50% for 10 wk | 50% for 14 wk | 50% for 24 wk | Tech – Ops |
| L3 Support | Remote | — | — | 50% for 24 wk | Tech – Ops |

# SECTION 14

## Estimated Person-Hours by Tier

The following table translates the staffing model into estimated person-hours, providing the basis for applying hourly or daily rates during financial proposal preparation.

| Role | Spark (hrs) | Boost (hrs) | Scale (hrs) | Location |
| --- | --- | --- | --- | --- |
| Program Manager | 560 | 720 | 800 | Local/Remote |
| Technical Project Manager | 400 | 480 | 560 | Remote |
| Tech Architect / Lead | 400 | 480 | 560 | Remote |
| Business Analyst / PM | 360 | 600 | 660 | Remote |
| DevOps Engineer | 360 | 600 | 660 | Remote |
| Full Stack Developer | 320 | 400 | 480 | Remote |
| QA / Tester | 240 | 320 | 400 | Remote |
| Service Delivery Lead | 200 | 280 | 480 | Remote |
| L1 Support | 400 | 560 | 960 | Remote |
| L2 Support | 200 | 280 | 480 | Remote |
| L3 Support | — | — | 480 | Remote |
| TOTAL | 3,440 | 4,720 | 6,520 |  |

These are baseline estimates. Service Providers should validate person-hours against the specific country context during procurement, including: number of use cases, integration complexity, data availability, and DPI Owner team maturity.

# SECTION 15

## Country Commitments for DaaS Engagement

The following commitments represent the minimum obligations that the country must fulfil to enable timely delivery, effective collaboration with the Service Provider, and long-term sustainability of the credentialing platform. These commitments apply across all three tiers.

| # | Commitment | Notes / References |
| --- | --- | --- |
| 1 | Designate a Focal Point with Decision-Making Authority Assign a dedicated focal point within the DPI Owner institution who holds decision-making authority or has a direct, documented reporting line to the relevant decision-maker. This individual will serve as the primary counterpart for the Service Provider and will be responsible for strategic alignment, institutional sign-offs, and escalation resolution throughout the engagement. |  |
| 2 | Assign a Program Manager with Dedicated Capacity Designate a program manager from the DPI Owner side with a minimum allocation of 20 hours per week dedicated to the project. This individual will coordinate day-to-day activities, track deliverables, manage internal stakeholders, and serve as the operational counterpart to the SP’s Program Manager. |  |
| 3 | Assign a Country Technical Team Establish a technical team on the country side to work alongside the SP during integration, testing, and deployment. At minimum, the team should include the following profiles: - Technical Lead / Architect — Oversees integration design and coordinates with the SP’s Technical Architect. - Systems / DevOps Engineer — Supports environment setup, infrastructure provisioning, and deployment activities. - Developer(s) — Participates in API integration, schema configuration, and customisation tasks. - QA / Testing Resource — Collaborates on UAT planning, test execution, and defect triage. | Roles may be combined in smaller teams, but the functional coverage must be ensured. These profiles mirror the SP’s staffing model (Section 13A) to enable effective collaboration. |
| 4 | Align Issuers and Verifiers Lead the coordination with all issuer institutions and verifying entities identified for the selected use cases. This includes formalising institutional agreements where necessary — such as LoIs, MoUs, or equivalent instruments — to secure their active participation in the rollout. |  |
| 5 | Ensure Data Readiness at the Issuer Level Ensure that each data provider (issuer) prepares and cleanses the underlying data to be credentialed. Issuers must expose the data through APIs, web services, or validated file-based mechanisms (CSV/Excel) that the SP can consume for credential generation. Data quality, completeness, and format compliance are the responsibility of the issuer, with guidance from the SP. |  |
| 6 | Conduct User Acceptance Testing (UAT) Organise and lead User Acceptance Testing in coordination with the SP. The DPI Owner is responsible for mobilising end users (issuers, verifiers, holders), providing test environments where applicable, and formally signing off on UAT results before go-live. |  |
| 7 | Comply with Institutional and Regulatory Requirements Ensure compliance with all applicable institutional, sectoral, and national regulations governing the deployment, including but not limited to: cybersecurity frameworks, data protection and privacy legislation, information security audits (VAPT), and any sector-specific approval processes required for credential issuance or verification. |  |
| 8 | Assign Resources for Hosting Upon Transition Commit to assuming hosting responsibilities at the end of the engagement period (8 months for Spark, 12 months for Boost/Scale). This includes provisioning infrastructure, assigning operational personnel, and ensuring budget continuity for cloud or on-premise hosting, monitoring, and support beyond the SP-provided hosting window. |  |
| 9 | Align Legal and Regulatory Framework Where required, lead the process of aligning or updating the domestic legal and regulatory framework to enable the issuance, storage, verification, and acceptance of verifiable credentials. This may include issuing internal decrees, executive orders, ministerial resolutions, or amendments to existing digital governance policies. |  |

# SECTION 16

## Indicative Cost Structure by Tier

The following table shows the relative weight of each cost category as a percentage of total engagement cost. These proportions serve as a benchmark for evaluating Service Provider proposals.

| Cost Category | Spark (%) | Boost (%) | Scale (%) |
| --- | --- | --- | --- |
| I. People Cost | 60–70% | 55–65% | 50–60% |
| II. Travel & Logistics | 8–12% | 8–13% | 8–12% |
| III. Infrastructure & Hosting | 6–10% | 8–12% | 10–15% |
| IV. Tooling & Licensing | 2–4% | 3–5% | 4–6% |
| V. Contingency / Flex | 15–20% of Cat. I | 15–20% of Cat. I | 15–20% of Cat. I |
| VI. AI Integration | Separate | Separate | Separate |

The shift from People Cost toward Infrastructure as tiers scale reflects longer hosting durations (8 months for Spark vs. 12 months for Boost and Scale) and increased multi-environment deployment complexity. Contingency is applied to People Cost only; as a proportion of grand total this represents approximately 8–13%.

# SECTION 17

## Payment Milestone Structure

Payments are tied to milestone-based deliverables aligned with the phased engagement model. The table below consolidates payment schedules across all three tiers for ease of comparison.

| Phase | Description | Spark % | Boost % | Scale % | Timing |
| --- | --- | --- | --- | --- | --- |
| A | Planning & Design | 20% | 15% | 10% | Wk 1–2 |
| B | Product Setup & Go-Live | 35% | 30% | 20% | Wk 3–10 |
| C | Execution & Scaling / Go-Live Stabilisation | 30% | 30% | 30% | Spark: Wk 11–14 ¦ Boost/Scale: Wk 11–24 |
| D | Transition & Closure / Ecosystem & Strategy | 15% | 10% | 15% | Spark: Wk 15–16 ¦ Boost/Scale: Wk 19–24 |
| E | Post-Rollout Support / Transition (Scale) | Incl. | 15% | 25% | Spark: Wk 17–32 ¦ Boost/Scale: Wk 25–48 |

Key differences: Spark compresses execution into a shorter stabilisation window (Wk 11–14) and bundles post-rollout support into the base cost. Boost and Scale spread execution over 14 weeks with a separate post-rollout payment. Scale runs denser parallel workstreams within the same 24-week active window as Boost, with ecosystem strategy and transition overlapping execution.

### 17A. Payment Conditions

Payments for each milestone are divided into two outcome categories:

Scope and delivery to production (70%): Verified completion of technical and programmatic deliverables.

Adoption and uptake (30%): Achievement of agreed adoption metrics (e.g., credentials issued, active users, verifications completed).

If milestone targets are not achieved primarily due to the Service Provider’s shortcomings, up to 20% of the relevant category’s payment may be withheld. The SP may earn back withheld amounts by achieving targets in the subsequent milestone.

# SECTION 18

## AI Integration Costing Guidance

AI readiness varies significantly across countries; bundling AI costs would either inflate prices for countries not ready or underestimate costs for those requiring advanced capabilities. As such, this section only serves as a suggestive guide on what to consider when handling costing for AI capabilities.

### 18A. Scoping Process

1. AI Readiness Assessment: Evaluate the country’s AI maturity, data privacy regulations, and hosting constraints during Planning & Design.

2. Capability Selection: Determine which AI-B and AI-U capabilities are feasible and desirable for the engagement tier.

3. Model Hosting Decision: Determine whether AI models will be hosted within country data residency (higher cost, better sovereignty) or via cloud-based AI services (lower cost, external dependency).

4. Local Partner Identification: Where cloud AI conflicts with data sovereignty, identify local AI/ML partners.

5. Cost Proposal: SP submits a separate AI cost proposal detailing additional person-hours, infrastructure, licensing, and operational costs.

### 18B. AI Cost Components

| Component | Examples | Cost Driver |
| --- | --- | --- |
| AI Engineering | ML engineers, data scientists, prompt engineers | Person-hours at Tech–Dev rates |
| AI Infrastructure | GPU compute, vector databases, model serving | Cloud GPU pricing, hosting duration, inference volume |
| AI API / Licensing | Commercial LLM APIs, NLP services, OCR, voice synthesis | Per-call pricing, monthly licensing, user volume |
| AI Governance | Bias auditing, transparency labelling, human-in-the-loop review | Audit frequency, compliance requirements |
| AI Operations (Ongoing) | Model monitoring, retraining, drift detection | Post-rollout duration, model complexity |

# SECTION 19

## Financial Proposal Template

Service Providers should structure their financial proposal according to the following template, provided as a companion spreadsheet.

Template: Togo_DaaS_SP_Proposal_Template.xlsx

Section 1 — People Cost: One row per role. Columns: resource location, resource type, number of units, estimated hourly rate (USD), estimated person-hours, estimated cost.

Section 2 — Travel & Logistics: Itemised: international travel per person-visit, hotel/accommodation per stay-day.

Section 3 — Infrastructure & Hosting: Cloud hosting for the tier duration: 8 months (Spark), 12 months (Boost), 12 months (Scale). Include compute, storage, networking, monitoring, security.

Section 4 — Tooling & Licensing: Third-party licences, ISV fees, notification gateways, testing tools.

Section 5 — Contingency / Flex: 15–20% of People Cost (Section 1).

Section 6 — AI Integration (if applicable): Separate cost proposal per Section 19 guidance.

Summary: Grand total excluding taxes, applicable tax rate, grand total including taxes.

# SECTION 20

## Costing Summary Comparison

| Dimension | Spark | Boost | Scale |
| --- | --- | --- | --- |
| Active Rollout | 16 weeks | 24 weeks | 24 weeks |
| Post-Rollout Support | 16 weeks | 24 weeks | 24 weeks |
| Total Engagement | ~8 months | ~12 months | ~12 months |
| Hosting Duration | 8 months | 12 months | 12 months |
| Use Cases at Go-Live | 2 end-to-end | 2–5 end-to-end | 5+ end-to-end |
| Estimated Person-Hours | ~4,080 | ~6,280 | ~8,140 |
| Roles Staffed | ~80% | ~90% | 90%+ |
| L3 Support Included | No | No | Yes |
| Outreach Manager | No | Yes | Yes |
| Payment Phases | 5 (A–E) | 5 (A–E) | 5 (A–E) |
| Contingency Range | 15–20% of People Cost | 15–20% of People Cost | 15–20% of People Cost |
| AI Integration | Separate | Separate | Separate |

This document is a working proposal and should be read alongside the DaaS Scope Document v2.0 and the DaaS Legal Framework. Feedback is welcome from all ecosystem stakeholders.